You are building a professional-grade Project Recovery & What-If Analysis engine for PMs and PMOs. This is not a toy scheduler. This must be logically correct, graph-driven, calendar-aware, and scenario-safe. Your job is to design the core computation engine + UI behavior, starting from two CSV inputs.

I want app which will help PMs, PMOs to take fix their project. This app take two csv file,

1. project_schedule.csv , containing schedule of project including resource allocation of task and other below attribute, this file will come from Planisware or ms project containing below columns

REQUIRED COLUMNS:

portfolio_name

project_id

project_name

project_description

activity_id -(1,2, etc.)

activity_name

activity_type (Milestones, Activity)

planned_start- (ISO dates (YYYY-MM-DD))

planned_finish- (ISO dates (YYYY-MM-DD))

planned_duration –(working days)

percent_complete (0–100)

predecessor_id- (Can be empty, Must reference valid activity_id,  Multiple predecessors, successors → delimiter (; with type like 3FS;5FS (in same task) or 2SS or 3FF or 4FS+1d etc.)

resource_id

fte_allocation (fte > 0, numeric, no upper bound)

OPTIONAL COLUMNS:

baseline_1_start- (ISO dates (YYYY-MM-DD))

baseline_1_finish- (ISO dates (YYYY-MM-DD))

baseline_1_duration–(working days)

actual_start- (ISO dates (YYYY-MM-DD))

actual_finish- (ISO dates (YYYY-MM-DD))

actual_duration-

constraint_type (can be blank or we can have data, start no earlier than, or finish no earlier than)

constraint_date(date corresponding to constraint type)

risk_impact

probability_percent

cost_impact_of_risk

delay_impact_days

Calculated Columns:

It will be blank by default in csv based app must calculated this to make other functionality of app work

es

ef

ls

lf

total_float_days

on_critical_path

baseline_load_hours- (in hours, working_days × resource_working_hours × fte_allocation)

remaining_duration

slip_days(an activity slipped from original plan)

cumulative_slip_days(due to chain reaction the total activity has slipped)

Computed delay metrics (core of your app)

Task-Created Delay (days)

Delay Carried In (days)

Total Schedule Delay (days)

Delay Absorbed (days)

Criticality Flag

Slips do not always add

Only the critical predecessor delay propagates

Parallel delays don’t stack

Non-critical delays shouldn’t count at all

PLANNED:

- planned_load_hours = planned_duration_days × resource_working_hours × fte

- planned_cost = planned_load_hours × resource_rate

ACTUAL:If percent_complete > 0:

- actual_load_hours =  actual_duration_days × resource_working_hours × fte

- actual_cost = actual_load_hours × resource_rate

FORECAST (REMAINING):If percent_complete < 100:

- remaining_load_hours =  remaining_duration_days × resource_working_hours × fte

- remaining_cost = remaining_load_hours × rate

EAC (Cost-only, no EVM yet):

- EAC_cost = actual_cost + remaining_cost

2. The second csv u will get is for resource related information = resource_cost_unit

REQUIRED COLUMNS:

- resource_id

- resource_rate

- resource_max_fte

- resource_start_date (when resource is onboarded, and can start working)

OPTIONAL COLUMNS (WITH DEFAULTS):

- resource_end_date (null = no limit)

- resource_working_hours (null = default = 8)

- resource_calendar (null= default = Mon–Fri)

- resource_holidays (list or empty)

- resource_skills

ADDITONAL INFORMATION FROM CSV

resource_name

resource_role

resource_holidays (if this is empty, no holiday he has reserved for himself)

6_day_working? If this this is true then resource is working 6 day in a week, (additional days off mentioned in resource_holidays, if its empty consider it false)

7_day_working? If this this is true then resource is working all days in a week (additional days off mentioned in resource_holidays, if its empty consider it false)

Just for the records columns, it will be coming from Planisware, dont touch this, this will coming from csv

successor_id

resource_name

role

Logical consistency

- planned_finish >= planned_start

- baseline_finish >= baseline_start

- percent_complete = 100 → actual_finish must exist

- Remaining duration = 0 when complete

- Add y

- our own logic if I am missing anything

Referential integrity

- predecessor_id exists in activity_id

- No self-dependencies

- No circular dependencies (DAG check)

If cycle exists → reject CSV
Do NOT “auto-fix” this. Ever.

ES, EF, LS, LF and Float should be calculated using the python.

- A Directed Acyclic Graph (DAG)

- Forward pass

- Backward pass

Python mental model

Each task = node
Each dependency = edge

You:

- Topologically sort the graph

- Forward pass → ES, EF

- Reverse order

- Backward pass → LS, LF

Extend this to SS / FF / SF + lags

Add calendar-aware ES/EF

Default calendar = 5d_8h (5 day working, with 8 hours per day)

Put this into a dependency graph

ES/EF/LS/LF + FS/SS/FF/SF + lags belong in a dependency graph

What the dependency graph actually represents

  - Nodes

- Each node = activity

- Node:

  - duration (working days)

  - calendar (Default calendar = 5d_8h)

  - ES, EF, LS, LF

  - Edges

- Each edge = constraint

- Edge:

  - predecessor

  - successor

  - type: FS / SS / FF / SF

  - lag (can be negative)

Correct architecture (burn this in)

CSV

↓

Build DAG (nodes + edges)

↓

Topological Sort (forward order)

↓

Forward Pass (ES / EF)

↓

Reverse Topological Sort

↓

Backward Pass (LS / LF)

↓

Float + Critical Path

How ES/EF fits into the graph: For each node, ES is constrained by incoming edges.

Create logic for that, the edge logic tells you how to compute ES.

for node in topo_order:

candidates = []

for edge in incoming_edges(node):

pred = edge.from_node

candidates.append(

compute_candidate_es(edge, pred, node)

)

node.ES = max(candidates) if candidates else project_start

node.EF = add_working_days(node.ES, node.duration)

Above is Pseudo-logic, you can create more optimized if required

Edge-aware ES calculation (this is the heart)

def compute_candidate_es(edge, pred, succ):

lag = edge.lag

if edge.type == "FS":

return add_working_days(pred.EF, lag)

if edge.type == "SS":

return add_working_days(pred.ES, lag)

if edge.type == "FF":

return add_working_days(pred.EF, lag - succ.duration)

if edge.type == "SF":

return add_working_days(pred.ES, lag - succ.duration)

raise ValueError("Invalid dependency type")

Above is Pseudo-logic, you can create more optimized if required

Calendars live outside the graph

Do NOT bake calendars into the graph structure.

Why?

- Different tasks may have different calendars

- Future: resource calendars

- Future: site calendars

Calendar is data, not topology.

Graph:

“Who depends on whom?”

Calendar:

“When can work happen?”

Separate them or suffer later.

Slip propagation = graph traversal

This is where your app actually becomes interesting.

If Task A slips by 2 working days:

- Update A.EF

- Recalculate successors via outgoing edges

- Propagate forward only where constraints tighten

That’s graph propagation, not full recompute.

If you recompute the whole schedule every time, you’ll choke on real portfolios.

Why NetworkX is your friend (for now)

import networkx as nx

G = nx.DiGraph()

- Nodes → tasks

- Edges → dependencies with attributes

- topological_sort() → forward pass order

- reverse() → backward pass

Later, you may replace it for performance.
For now, it’s perfect.

Brutal warning

If your dependency graph:

- Stores dates as integers

- Ignores calendars

- Treats all edges as FS

- Can’t handle negative lag

- Allows cycles

Then your engine is fundamentally wrong.

No amount of UI, Streamlit polish, or “AI recommendations” will save it.

2. resource_cost_unit.csv

resource_cost_unit.csv containing resource information with their availability, cost, FTE, Dates available, calendar holidays, using this information the cost of projects will be calculated. The columns are below

referring to above resource_cost_unit.csv and project_schedule.csv u need to calculate the activity and project cost attribute also, for example, actual cost, activity duration is 10 days, resource worked for 8 hours, total load=80, then if rate is 10 dollars per hour then total cost = 800 dollars. The app should calculate planned, actual, baseline cost with this.

After calculating cost you need to do eva for below

- PV

- EV

- AC

- BAC

- CV = EV – AC

- SV = EV – PV

- VAC= BAC – EAC

- CPI= EV/AC

- SPI= EV/PV

- EAC (For this calculate all, but gives user option which one they want to see)

- EAC= BAC/CPI (If the CPI is expected to be the same for the remainder of the project)

- EAC= AC + BAC – EV (If future work will be accomplished at the planned rate)

- EAC = AC + Bottom-up ETC (If the initial plan is no longer valid)

- EAC = AC+ [(BAC – EV)/ (CPI x SPI)] (If both the CPI and SPI influence the remaining work)

- ETC = EAC – AC

- TCPI = (BAC– EV)/(BAC – AC)(The efficiency that must be maintained in order to complete on plan)

- TCPI = (BAC – EV)/(EAC – AC)(The efficiency that must be maintained in order to complete the current EAC.)

Main UI and tabs

PMs think in this order:

- Are we screwed? (Status)

- Why? (Root cause)

- What can I do? (Recovery options)

- What happens if I do it? (Impact)

- Can I undo it? (Scenario control)

Your UI must enforce this flow.

PROJECT HEALTH STRIP (Always Visible)

Tabs: [Overview] [Schedule] [Resources] [Cost][Export][Scenarios]

Change Preview Bar (Always Visible)

1️⃣ TOP: PROJECT HEALTH STRIP (Sticky)

This is NOT a dashboard. This is situational awareness.

Metrics (single line, brutal clarity)

- 🔴 / 🟡 / 🟢 Overall Project Status

- Finish Variance (days)

- Cost Variance ($)

- % Activities on Critical Path

- Peak Resource Overload (max FTE > cap)

- Risk Exposure ($ = probability × impact)

Clicking any metric jumps to the relevant tab and auto-filters.

2️⃣ TAB 1: OVERVIEW (Read-only, diagnosis only)

Filter to narrow down which project to select, if not selected show all the projects analyzed from csv

Purpose: Explain why the project is broken.
No edits allowed here.

A. Network Summary Panel (Top)

- Total activities

- Total dependencies

- DAG validity ✔️ / ❌

- Longest path length

- Number of hard constraints

If DAG ❌ → hard stop. Disable everything. No recovery until fixed externally.

B. Critical Path Viewer (Center)

- Dependency Graph (Interactive)

  - Nodes = activities

  - Red = critical

  - Grey = non-critical

- Clicking a node highlights:

  - Predecessors

  - Successors

  - Float

  - Risk impact

You must show the graph here, not buried in Schedule tab.

C. Root Cause Table (Bottom)

A ranked table answering “why are we late / over budget?”

Columns:

- Cause Type (Resource / Dependency / Constraint / Risk)

- Activity ID

- Description

- Impact Days

- Impact Cost

- Confidence %

This table feeds the recovery engine. If this is weak, your app is weak.

3️⃣ TAB 2: SCHEDULE RECOVERY (This is where PMs live)

Schedule tab:

Every “bad schedule” boils down to four root causes:

- Critical path slippage

- Negative float

- Broken logic (dependencies)

- Unrealistic durations / calendars

If your tab doesn’t address all four, it’s incomplete.

Clear definitions (no ambiguity)

1️⃣ Net Task Slip (earlier concept)

What it meant conceptually:

“How much delay did this task add after accounting for upstream delay?”

Formula

Net Task Slip = Task-Created Delay − Delay Carried In

Interpretation

- > 0 → Task made the schedule worse

- = 0 → Task neither helped nor hurt

- < 0 → Task helped recover schedule

2️⃣ Delay Absorbed (new, better metric)

What it means:

“How much upstream delay did this task absorb or neutralize?”

Formula

Delay Absorbed = Delay Carried In − Task-Created Delay

What the Schedule Recovery tab must show (non-negotiable)

A. “Why is my project late?”

Top section. No interaction yet.

Show:

- Planned finish vs current finish

- Total slip (working days)

- Cumulative Predecessor Slip (days)

- % of slip coming from:

  - Critical path delay

  - Logic constraints

  - Calendars

If you can’t explain the cause, don’t recommend fixes.

B. “Which activities are killing me?”

This is where amateurs list “late tasks”. That’s useless.

You must show impact-ranked activities.

For each activity:

- On critical path? (Y/N)

- Total float (negative included)

- Slip contribution (days)

- Downstream impact count

- Dependency type causing constraint (FS/SS/FF/SF)

Sorted by:

“Fix this first or don’t bother.”

4️⃣ TAB 3: RESOURCE RECOVERY (Where projects actually fail)

LEFT: Resource Load Panel

A. Resource Utilization Heatmap

- Rows: Resources

- Columns: Time (week/month)

- Red = overload

- Blue = underutilized

Click a red cell → auto-filter task list.

B. Resource Assignment Table

Columns:

- Resource Name

- Role

- Max FTE

- Assigned FTE

- Overload %

- Cost Rate

Resource Recovery Workbench

A. Suggested Resource Fixes

Each row:

- Action Type (Replace / Split / Reduce FTE)

- From Resource → To Resource

- Skill Match %

- Cost Delta

- Schedule Impact

Your app MUST justify replacements via:

- resource_skills

- resource_max_fte

- availability window

B. Allocation Editor (Controlled)

- Slider for FTE

- Date window selector

- Live recalculation of:

  - Duration

  - Cost

  - Successor impact

5️⃣ TAB 4: COST RECOVERY (For PMOs & Sponsors)

Cost Breakdown

A. Cost Waterfall

- Baseline → Planned → Actual → EAC

- Variance bars

B. Cost Drivers Table

Ranked by impact:

- Activity ID

- Resource

- Cost Overrun

- Root Cause

Cost Recovery Actions

A. Cost Reduction Options

Trigger

- Forecast cost > budget

Actions

- Resource downgrading

  - Replace expensive resource with cheaper skill-equivalent

  - Recalculate cost impact

- Reduce allocation

  - Increase duration but reduce cost burn

- Scope reduction

  - Remove or defer tasks

  - Immediate cost delta shown

Rows like:

- Replace Resource A ($120/hr) → B ($80/hr)

- Reduce allocation from 1.0 → 0.7

- Defer Task X (Phase 2)

Each action shows:

- Cost Delta

- Finish Impact

- Risk Impact

What-If Cost Scenarios (This is where your app becomes dangerous)

PM selects:

- Replace Resource A with B

- Reduce allocation by X

- Delay task by Y

Your app:

- Clones scenario

- Shows delta:

  - Finish date

  - Total cost

  - Peak burn month

6️⃣ CHANGE MANAGEMENT (BOTTOM BAR – ALWAYS VISIBLE)

Change Preview Bar

- of modified activities

- Finish date delta

- Cost delta

- Risk delta

Buttons:

- ✅ Apply to Scenario

- 🔄 Undo

- 📤 Export CSV (strict schema, no surprises)

No silent writes. Ever.

Whenever I apply recovery from each tab, the table here should be highlighted, what got changed, and ready to be exported

7️⃣ SCENARIOS (YOU NEED THIS OR DON’T BOTHER)

- Default: Current Forecast

- Scenarios:

  - “Aggressive Recovery”

  - “Cost Neutral”

  - “Low Risk”

Each scenario:

- Isolated data copy

- Switchable

- Exportable

PMOs will love you for this.

4️⃣ CROSS-DIMENSION RECOVERY (This is the killer feature)

Most tools stop at “resource” or “schedule”. You combine all three.

Example Recovery Playbooks

Your app should literally offer buttons like:

- “Fix overallocation with minimal cost impact”

- “Recover milestone with least scope reduction”

- “Reduce cost overrun without extending finish date”

Behind the scenes:

- Run heuristic:

  - Try resource swap

  - Try allocation change

  - Try fast-track

  - Rank outcomes